| Project No. | : | NDICI-THE-NEAR/2023/451-643 |
| --- | --- | --- |
| Project Name | : | Empowering Syrian Women through Art and Culture: A Project for Gender Equality |
| Grant Recipient | : | Flying Broom Foundation |
| Name of the Tender | : | Workshop Services Purchase |
| Tender Number | : | 2025/WeART/05 |

1.	BACKGROUND

1.1.	General information about your project

Funded by the European Union Delegation to Syria and implemented in partnership with the Flying Broom Foundation and the Anatolia Youth Federation, the Empowering Syrian Women through Culture and Arts: Gender Equality Project aims to defend the rights of women and girls in Syria, promote gender equality through arts and culture, and strengthen civil society structures.

Activities in this project, planned to last 24 months, will be carried out in two types: physical and digital. Physical activities will take place in Aleppo, Idlib, Ankara, and Gaziantep, while the digital component will also extend to other regions of Syria, such as Damascus, Homs, and Hama. Capacity-building trainings, workshops, seminars, and meetings will be organized within the scope of the project to achieve its objectives.

1.2.	Contracting Authority

Flying Broom Foundation

2.	OBJECTIVES

2.1	Results expected to be achieved by the service provider

3.	SCOPE OF WORK

3.1	Items to be purchased in the service procurement tender:

6.10 Organization of Creative Expression Workshop

6.11 Organization of Music Workshop: "My Song, Your Song"

6.12 Organization of Drama Workshop “Seeing you in me and me in you”

6.13 Organization of Photography Workshop "Inclusive photography-Her Lens"

6.14 Short Film Production Workshop

6.16 Gender-Sensitive & Inclusive Media Training for Youth

3.2.	Detailed list of activities

3.2.1 Organization of Creative Expression Workshop

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 3 days.

- Face-to-face training will be provided to a total of 30 people, with at least 15 people in Northern Aleppo (Afrin) and 15 people in Idlib.

- The room will be equipped with 1 laptop computer, a projector, and a microphone for the trainer's use.

- Participants will be provided with lunch every day. Lunch will consist of soup, red meat, rice, salad, dessert, and beverages. For vegetarian and vegan preferences, please inform us at least 2 days in advance, and those menus will also be available on the event day.

- There will be two coffee breaks each day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (training plan, pre-test/post-test, training evaluation questionnaire, training presentation, training report) will be prepared by the trainer. The service provider must reproduce the necessary training materials in quantities appropriate for the number of participants.

- Stationery products to be used in workshop activities will be provided.

- A facilitator will be present in the workshop throughout the workshop program. Detailed information can be found in section 5.1 Personnel. In addition, 2 dance instructors will also participate.

- A participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and methodology used by the participants in Arabic will be published on the project website.

3.2.2 Organization of Music Workshop

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 3 days.

- Face-to-face training will be conducted with a total of 30 people, including at least 15 people in North Aleppo (Afrin) and 15 people in Idlib.

- The room will be equipped with 1 laptop computer, a projector, and a microphone for the trainer's use.

- Participants will be provided with lunch each day. Lunch will include soup, red meat, rice, salad, dessert, and beverages. For vegetarian and vegan preferences,

will be provided to us at least 2 days in advance, and those menus will be prepared on the day of the event.

- There will be two coffee breaks per day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (training plan, pre-test/post-test, training evaluation survey, training presentation, training

report) will be prepared by the trainer. The service provider must reproduce the necessary training materials in quantities appropriate to the number of participants.

- Stationery products to be used in workshop activities will be provided.

- A facilitator will be present in the workshop throughout the workshop program. Detailed information can be found in section 5.1 Personnel. In addition, 2 music instructors will also participate.

- A participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and the methodology used by the participants in Arabic will be published on the project website.

3.2.3 Organization of Drama Workshop / Drama Workshop Organization

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 3 days.

- Face-to-face training will be conducted with a total of 30 people, including at least 15 people in North Aleppo (Afrin) and 15 people in Idlib.

- The room will be equipped with 1 laptop computer, a projector, and a microphone for the trainer's use.

- Participants will be provided with lunch every day. Lunch will consist of soup, red meat, rice, salad, dessert, and drinks. For vegetarian and vegan preferences, information must be provided to us at least 2 days in advance, and those menus will be prepared on the day of the event.

- There will be two coffee breaks per day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (training plan, pre-test/post-test, training evaluation questionnaire, training presentation, training report) will be prepared by the trainer. The service provider must reproduce the necessary training materials in quantities appropriate to the number of participants.

- Stationery products to be used in workshop activities will be provided.

- A facilitator will be present in the workshop throughout the workshop program. Detailed information can be found in section 5.1 Personnel. In addition, 2 drama instructors will also participate.

- A participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and the methodology used by the participants in Arabic will be published on the project website.

3.2.4 Organization of Photography Workshop

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 3 days.

- Face-to-face training will be conducted with a total of 30 people, including at least 15 people in Northern Aleppo (Afrin) and 15 people in Idlib.

- The room will be equipped with 1 laptop computer, a projector, and a microphone for the trainer's use.

- Participants will be provided with lunch each day. Lunch will include soup, red meat, rice, salad, dessert, and beverages. For vegetarian and vegan preferences, we request that you inform us at least

- 2 days in advance, and those menus will be prepared on the day of the event.

- There will be two coffee breaks each day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (educational plan, pre-test/post-test, educational evaluation questionnaire, educational presentation, educational report) will be prepared by the trainer. The service provider must reproduce the materials necessary for the training in quantities appropriate to the number of participants.

- Stationery products to be used in workshop activities will be provided.

- A facilitator will be present in the workshop throughout the workshop program. Detailed information can be found in section 5.1 Personnel. In addition, 2 producers and a film producer will also participate.

- A participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and methodology used by the participants in Arabic will be published on the project website.

3.2.5 Short Film Production Workshop

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 5 days.

- Face-to-face training will be conducted with a total of 30 people, including at least 15 people in Northern Aleppo (Afrin) and 15 people in Idlib.

- The room will be equipped with 1 laptop, a projector, and a microphone for the trainer's use.

- Participants will be provided with lunch every day. Lunch will consist of soup, red meat, rice, salad, dessert, and drinks. For vegetarian and vegan preferences, information must be provided to us at least 2 days in advance, and those menus will be prepared on the day of the event.

- There will be two coffee breaks per day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (training plan, pre-test/post-test, training evaluation questionnaire, training presentation, training report) will be prepared by the trainer. The service provider must reproduce the necessary training materials in quantities appropriate to the number of participants.

- Stationery products to be used in workshop activities will be provided.

- A facilitator will be present in the workshop throughout the workshop program. Detailed information can be found in section 5.1 Personnel. In addition, 2 producers and a film producer will also participate.

- A participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and methodology used by the participants in Arabic will be published on the project website.

3.2.6 Gender-     -Sensitive & Inclusive Media Training for Youth

- The workshop will be held at the hotel or in a meeting room previously notified to us and approved.

- Each workshop will last 1 day.

- Face-to-face training will be provided to a total of 75 people: at least 25 people in North Aleppo (Afrin), 25 people in Idlib, and 25 people in Aleppo.

- The room will be equipped with 1 laptop, a projector, and a microphone for the trainer to use.

- Participants will be provided with lunch each day. Lunch will consist of soup, red meat, rice, salad, dessert, and beverages. For vegetarian and vegan preferences, information must be provided to us at least 2 days in advance, and those menus will be prepared on the day of the event.

- There will be two coffee breaks per day, one before noon and one after noon. Sweet/savory pastries will be served.

- Educational materials covering self-expression and creative activities (training plan, pre-test/post-test, training evaluation questionnaire, training presentation, training report) will be prepared by the trainer. The service provider must reproduce the necessary training materials in quantities appropriate to the number of participants.

- Stationery products to be used in workshop activities will be provided.

- The trainer will be present in the workshop throughout the workshop program. Detailed information is provided in section 5.1 Personnel.

- The participant list, photos, videos, and KVKK approval documents will be submitted to the Field Coordinator to be added to the training report.

- A short video explaining the transformation process and methodology used by the participants in Arabic will be published on the project website.

3.3	Outputs and Results

Outputs:

Firstly, the training materials prepared at the end of each workshop, participant lists, pre-test and post-test results, and training reports will be tangible outputs. Participants will have experienced activities that will enable them to express themselves, develop their creativity, and acquire new skills during the training. Materials used in the workshops, stationery products, photo and video recordings, and short videos prepared in Arabic will also be among the documented outputs of the activities. Roundtable meetings will be sessions where relevant stakeholders come together to discuss topics identified within the scope of the project, share their experiences, and develop joint solutions.

Results:

In terms of results, it is expected that participants will gain new skills in the areas of artistic expression and creativity, become more socially and culturally active, and strengthen their individual self-confidence. The workshops will also increase social solidarity and improve communication and cooperation among participants. Learning outcomes, measured through training reports and evaluation surveys, will demonstrate the project's effectiveness; short videos published on the project website will ensure transparency and visibility of the process. Thus, the activities will produce lasting results that contribute to individuals' personal development and support cultural interaction and social cohesion among communities. Furthermore, the reports, recommendations, and joint decisions prepared as a result of the meetings will emerge as concrete outputs; this process will contribute to the sustainability of the project by strengthening inter-institutional cooperation.

4. LOGISTICS AND TIMING

4.1.	Location

The trainings will be conducted in person in Idlib, Afrin, and Aleppo.

4.2.	Start Date and Duration of Employment

The start date of the work is the day following the date on which the contract is signed by both parties, and the work covered by the service procurement must be completed by October 2025 at the latest.

- 6.10 Organization of Creative Expression Workshop: The activity will be completed in September. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

- 6.11 Organization of Music Workshop: "My Song, Your Song": The activity will be completed in October. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

- 6.12 Organization of Drama Workshop “Seeing you in me and me in you” The activity will be completed in October. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

- 6.13 Organization of Photography Workshop "Inclusive Photography-Her Lens": The activity will be completed in October. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

- 6.14 Short Film Production Workshop: The activity will be completed in November. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

- 6.16 Gender-sensitive & Inclusive Media Training for Youth: The activity will be completed in November. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins. Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins.

Training materials will be delivered to the Contracting Authority's field coordinators in Idlib and Afrin one week before the training begins. Dates may be changed by the Contracting Authority due to circumstances that may arise during the project implementation process. These changes will be communicated to the service provider at least 10 days in advance.

5.	REQUIREMENTS

5.1.	Equipment and facilities to be provided by the service provider.

Equipment purchase is not possible under this contract.

5.2.	Personnel.

The CVs of personnel (key experts) are requested along with the technical proposal.

5.2.1 Creative Expression Workshop

- Must have training in dance, body-based work, performance arts, or related fields, or possess verifiable professional experience.

- At least 3 years of experience in creative expression, body-based work, or art-focused workshops

- Experience in conducting group-based workshops or training

- Education in creative movement, body awareness, or art-based education (preferred)

- Arabic verbal communication skills (preferred)

5.2.2 Music Workshop

- Education or professional experience in music, voice, rhythm, instruments, or related fields

- At least 3 years of experience in conducting music-based education or workshops

- Experience in conducting group-based activities

- Training in music pedagogy, creative music, and rhythm studies (preferably)

- Arabic language communication skills (preferably)

5.2.3 Drama Workshop / Drama Workshop

- Education in drama, theater, performing arts, or creative drama, or experience in a related field

- At least 3 years of experience in drama or theater-based workshops/training

- Experience in conducting participant-based drama and improvisation workshops

- Training in creative drama, applied theater, or forum theater (preferred)

- Arabic verbal communication skills (preferably)

5.2.4 Photography Workshop

- Education or professional experience in photography, visual media, filmmaking, or related fields

- At least 3 years of workshop/training experience in photography or visual storytelling

- Experience in conducting training or workshops

- Training in documentary photography, visual storytelling, or media production (preferred)

- Arabic communication skills (preferred)

5.2.5 Short Film Production Workshop

- Education in film production, video production, or media, or verifiable professional experience

- At least 3 years of experience in film production or video production

- Experience in conducting practical workshops or training

- Training in short film, documentary production, or digital media (preferred)

- Arabic language communication skills (preferably)

5.2.6 Gender-sensitive & Inclusive Media Training

- Bachelor's degree in communication, media, journalism, social sciences, or a related field, or equivalent professional experience

- At least 3 years of work experience in the field of gender equality, inclusive media, or human rights

- Experience in conducting training or workshops

- Training or certifications in gender education, media ethics, or human rights (preferred)

6.	MANAGEMENT/CONTROL AND FINAL APPROVAL

6.1.	Controller

Ayşe Ürün Güner

Board Member

7.	VISIBILITY

The Service Provider must perform the expected work in accordance with EU visibility rules. The Contracting Authority will communicate the relevant visibility rules to the Service Provider, and the necessary work and procedures will be carried out with the approval of the Contracting Authority.